## Definitions
Risk Log Data Element | Definition
Project Title | Identifies the project title associated with the identified risk Note: If the risk impacts multiple projects, then leave blank. If left blank, then the risk will be reported as a Program Level Risk. A program level risk is a risk that could impact more than one project.)
Risk Title | Unique name given to an identified risk
Risk Description | A brief statement giving the characteristics (e.g., cause and time-window) of the identified risk
Risk Impact | Describes the potential impact of the risk/the effect it will have on the project, program, program area or portfolio
Risk Category | A dropdown list of risk categories: - External Risk: Includes regularity, environmental, or governmental issues; market shifts; problems with project sites, etc. - Internal Risk: Includes changes to schedule or budget; scope changes; inexperienced team members; issues with people, staffing, materials, and equipment, etc.
Probability of Occurrence (H,M,L) | A dropdown 3-point Likert scale (i.e., High, Medium, Low) used to estimate the probability of an identified risk occurring
Level of Impact (H,M,L) | A dropdown 3-point Likert scale (i.e., High, Medium, Low) used to estimate the potential impact of identified risks
Mitigation Plan | A plan to manage, eliminate, or limit the impact of risks
Date Last Assessed (MMM-YY) | Last date the team assesses a risk. Use the first three letters of the month and the last two numbers of the year Note: After a risk has been identified, it is recommended to reassess that risk periodically
Status | A dropdown list of risk statuses: - Identified: Represents risks that are new to the risk log and could potentially prevent a project/program from achieving its objectives - Mitigation In Progress: Represents risks that have been realized and are actively being mitigated - Resolved: Represents risks that no longer pose a threat to achieving project/program objectives
Notes | Reserved for additional notes related to a risk (e.g., updates)

## ITS4US
Project Title (If left blank, then the risk will be reported as a Program Level Risk) | Risk Title | Risk Description | Risk Impact | Risk Category | Probability of Occurrence | Level of Impact | Mitigation Plan | Date Last Assessed (MMM-YY) | Status | Notes
ITS4US Technical Support (FY25) | Phase 3 Technical Support Needs | Due to delays in sites moving to Phase 3 and delays in sites completing Phase 3 deliverables, it may require additional technical assistance and program management resources to support Phase 3 activities. | Site deployment delays may require additional technical assistance. | External | Medium | Medium | The program is monitoring funds spent for technical assistance and program management resources by site. | 2026-08-26 | Mitigation in Progress | All four sites are now in Phase 3. Technical support needs for Phase 3 are still being assessed and will be reported next month.
ITS4US Technical Support (FY25) | Phase 2 Technical Support Needs | Delays in completing Phase 2 requirements for two of the sites may require additional technical assistance and program management resources. | Delays in completion of Phase 2 may require additional technical assistance. | External | High | Medium | The program is monitoring funds spent by site to track level of technical assistance support by site. | 2026-12-25 | Resolved | All four sites are now in Phase 3.